## 📋 Instructions
PRODUCT ROADMAP PROCESS TOOLKIT
Sempiterno Solutions · sempiternosolutions.com
WHAT IS THIS TOOLKIT?
This toolkit gives you a repeatable process for building a product roadmap that your team will actually follow. It is not a list of features — it is a decision-making framework. Work through the three tabs in order: Instructions (this tab), Example (a filled-in sample), then Worksheet (your blank copy to complete).
THE 6-SECTION PROCESS
1 | Product Overview
Name, one-sentence vision, target users, and current stage. Everything else in the roadmap must serve this vision. If an initiative does not, cut it.
2 | Goals & Success Metrics
3 time-bound goals and one North Star Metric. Goals must be measurable. 'Improve the product' is not a goal. 'Reduce onboarding time from 5 days to 2 days by Q2' is.
3 | Initiatives & Priorities
8–12 initiatives maximum, each assigned a priority (High / Medium / Low), a delivery quarter, and an owner. If you have more than 12, you have a wish list — not a roadmap.
4 | What's NOT on the Roadmap
Document what you deliberately excluded and why. This is the most underrated section. It prevents the same debates restarting every quarter.
5 | Stakeholders & Review Cadence
Who owns the roadmap, who has input, and how often it is reviewed. Monthly reviews are right for most teams. Quarterly is the minimum.
6 | Risks & Dependencies
The 2–3 things most likely to cause a slip. Name them early so you can manage them, not discover them when it's too late to recover.
GOLDEN RULES
✦ | A roadmap is a bet, not a commitment. Communicate it as such.
✦ | If stakeholders can't see the logic from vision → goal → initiative, the roadmap will not hold.
✦ | Update the roadmap every 4–6 weeks, not every sprint.
✦ | Say no to good ideas. Every 'yes' is a 'no' to something already on the list.
✦ | The team building the work must have input into the roadmap. Roadmaps built in isolation get ignored.
© 2026 Sempiterno Solutions · sempiternosolutions.com · All rights reserved

## ✅ Example
EXAMPLE — Client Portal Product Roadmap
Filled-in example to show you how a completed roadmap looks.
1 — PRODUCT OVERVIEW
Product / Project Name | Sempiterno Client Portal
Vision | Give every retainer client a single place to track deliverables, review reports, and request changes — without email chains.
Target Users | Existing Sempiterno retainer clients — founders and marketing managers at 7-figure eCommerce brands.
Current Stage | Discovery
2 — GOALS & SUCCESS METRICS
Goal 1 | Q2 2026 — Reduce client onboarding time from 5 days to 2 days.
Goal 2 | Q3 2026 — 80% of active clients logging in at least once per week.
Goal 3 | Q4 2026 — Net Promoter Score above 50 from portal users.
North Star Metric | Weekly active clients in the portal
What 'done' looks like | All retainer clients onboarded, weekly logins are the default behaviour, and the support inbox drops by at least 40%.
3 — INITIATIVES & PRIORITIES
Initiative | Description | Priority | Quarter | Owner | Status
Client dashboard — deliverables view | Card view showing all active deliverables by status. | High | Q2 | Jacob G. | In Progress
Report upload & version history | Clients can view and download any report, any version. | High | Q2 | Dev Lead | Planned
In-app change request form | Replace email chains with a structured form. | Medium | Q3 | Jacob G. | Planned
Automated weekly digest email | Summary of progress sent every Monday morning. | Medium | Q3 | Dev Lead | Backlog
Client usage analytics (internal) | Track logins, views, and engagement for our team. | Low | Q4 | Jacob G. | Backlog
Mobile-optimised view | Responsive layout pass for phone and tablet. | Low | Q4 | Dev Lead | Backlog
4 — WHAT'S NOT ON THE ROADMAP
Idea / Feature | Reason for Deferring
Native iOS / Android apps | Web-first covers 95% of use cases. Revisit after the web portal hits 80% weekly active client rate.
AI-generated report summaries | Interesting but speculative. No validated demand yet. Moved to next planning cycle.
5 — STAKEHOLDERS & REVIEW CADENCE
Roadmap Owner | Jacob Gerrish — final call on all priority changes.
Key Stakeholders | Engineering lead, Head of Client Success, Founder.
Review Frequency | Monthly — first Monday of each month. Major re-prioritisation at quarter boundaries only.
How Changes Get Proposed | Any stakeholder submits a request via shared Notion doc. Changes require roadmap owner sign-off before being added.
6 — RISKS & DEPENDENCIES
Risk 1 | Auth provider integration may need 3rd-party legal review — buffer 2 weeks in Q2 timeline.
Risk 2 | Design resource is shared with another product — Q3 may slip if prioritisation conflicts.
External Dependency | Data warehouse migration (ops team, targeting Q2 completion) must finish before the reporting module can be built.
© 2026 Sempiterno Solutions · sempiternosolutions.com

## 📝 Worksheet
YOUR PRODUCT ROADMAP — WORKSHEET
Fill in every section. Refer to the Instructions tab if you get stuck.
1 — PRODUCT OVERVIEW
Product / Project Name
Vision (one sentence)
Target Users
Current Stage | Discovery / Alpha / Beta / Live / Scaling ← delete as applicable
2 — GOALS & SUCCESS METRICS
Goal 1 (Q__ 20__)
Goal 2 (Q__ 20__)
Goal 3 (Q__ 20__)
North Star Metric
What 'done' looks like
3 — INITIATIVES & PRIORITIES (8–12 max)
Initiative | Description | Priority (High/Med/Low) | Quarter | Owner | Status
4 — WHAT'S NOT ON THE ROADMAP
Idea / Feature | Reason for Deferring
5 — STAKEHOLDERS & REVIEW CADENCE
Roadmap Owner
Key Stakeholders
Review Frequency
How Changes Get Proposed
6 — RISKS & DEPENDENCIES
Risk 1
Risk 2
Risk 3
External Dependencies
© 2026 Sempiterno Solutions · sempiternosolutions.com